## Sheet1
S.No | Activity | Start Date | End Date | Status
1 | Setup connectivity between ISC & GitHub | 26th Oct | 30th Oct | In-Progress
2 | Setup up file directory structure | 2nd Nov | 14th Nov | Yet to Start
3 | Application creation setup - SQL Loader | 16th Nov | 30th Nov | Yet to Start
4 | Application creation setup - File Based | 1st Dec | 7th Dec | Yet to Start
5 | Application creation setup - AD | 8th Dec | 18th Dec | Yet to Start
6 | Application creation setup - JDBC | 4th Jan | 15th Jan | Yet to Start
7 | Application creation setup - API | 18th Jan | 29th Jan | Yet to Start
8 | Application creation setup - Windows & Linux | 1st Feb | 12th Feb | Yet to Start